## Work Summary
Date | Work Done | Man Hours
Jan 1-2 | Project setup, Firebase integration | 4
Jan 2-3 | Core video player implementation | 3.5
Jan 3-4 | Video sync service development | 3
Jan 4-5 | Camera & recording infrastructure | 4
Jan 5-6 | Clip browser screen | 2.5
Jan 6 | UI scaffolding & navigation | 2.5
Jan 7 | PageView implementation | 2
Jan 8-9 | Compilation error fixes & cleanup | 1.5
Jan 9 | Video looping bug fix | 2
Jan 10 | Video sizing – screen fill implementation | 2.5
Jan 10 | Video preloading on app start | 1.5
Jan 11 | Clip recording – save only on video end | 2
Jan 11 | Auto-recovery for corrupted videos | 2
Jan 12-13 | DocId assignment for saved clips | 3
Jan 13 | Enhanced logging for debugging | 1
Jan 14 | Dot indicator for video navigation | 1.5
Jan 14-15 | Code structure restoration | 1.5
Jan 15-17 | UI/UX refinements | 2